## Sheet1
Date
Product Search Page | NO | 2017-08-10
Paginated search | NO | 2017-08-10
Update database with products | NO | 2017-08-10
Add itemID to database only when user clicks addtoCart | NO | 2017-08-10
Create Category Database from Taxanomy API | NO | 2017-08-10
Populate categories and subcategories in home page and in search box | NO | 2017-08-10
Paginated Search when clicking categories using Paginated API | NO | 2017-08-10
Update database with categories | NO | 2017-08-10
2017-08-10
login | NO | 2017-08-10
authentication using facebook,google | NO | 2017-08-10
2017-08-10
User Activities | NO | 2017-08-11
cart CRUD | NO | 2017-08-11
wishlist CRUD | NO | 2017-08-11
load/update profile page | NO | 2017-08-11
Followers R | NO | 2017-08-11
Following CRUD Request | NO | 2017-08-11
Address CRUD | NO | 2017-08-11
payment CRUD | NO | 2017-08-11
Reviews CRUD | NO | 2017-08-11
message CRUD | NO | 2017-08-11
order CRUD | NO | 2017-08-11
visitor prodile | NO | 2017-08-11
replying to other's reviews | NO | 2017-08-11
discovering other users | NO | 2017-08-11
2017-08-11
Templates | NO | 2017-08-12
Pages tested for Mobile View | NO | 2017-08-12
Customer list for Manager to block | NO | 2017-08-12
All user list for admin to CRUD operation | NO | 2017-08-12
all product list for admin/manager to CRUD | NO | 2017-08-12
2017-08-12
role | NO | 2017-08-12
restrictions based on roles | NO | 2017-08-12
anonymous user support- add to cart/add review | NO | 2017-08-12
2017-08-12
2017-08-13
Home Page | NO | 2017-08-13
contents | NO | 2017-08-13
design | NO | 2017-08-13
| NO | 2017-08-14
Final features | NO | 2017-08-14
Pages looks improvement | NO | 2017-08-14
NO

## Sheet2
Firstlevel_ID | SecondLevel_ID | ThirdLevel_ID